## Timeline
Task
By EOD: |  | Ashleigh | Mark | Terrell
2021-06-12 | Complete API List | check
Access to all APIs
Project Plan
Project Proposal
2021-06-14 | Data types determined |  |  | done
“Napkin’ sketch figures
2021-06-15 | API Homework code complete
2021-06-16 | Data gathered
2021-06-17 | Figures printed
2021-06-18 | Figures complete
2021-06-19 | Analysis complete
2021-06-20 | Clean code
*Happy Dad's Day!*
2021-06-21 | Presentation created
2021-06-22 | Run through complete
Final proof
2021-06-23 | Present!

## Data Sources
APIs
Social Media | Cryptocurrency |  | Stock Market
Twitter | Google Finance |  | Google Finance
Reddit |  | Bitcoin |  | NASDAQ
LinkedIn |  | Ethereum |  | Dow Jones
Tether
Cardano
Dogecoin